## Projects
Key | Name | PercentComplete | LastUpdated | Customer
ORB-1001 | Nordic Retail Platform | 40 | 2026-07-01 | Nord Retail Group
ORB-1002 | Customer Data Migration | 65 | 2026-06-15 | Fjord Bank
ORB-1005 | Payments Compliance Upgrade | 72 | 2026-06-10 | Fjord Bank

## Milestones
ProjectKey | Name | DueDate | CompletedDate | Status | DependsOn | BaselineDate | IsCritical
ORB-1001 | POS pilot live | 2026-07-31 |  | In Progress |  | 2026-07-15 | true
ORB-1002 | Data cutover dress rehearsal | 2026-07-18 |  | Missed |  | 2026-05-30 | true
ORB-1005 | SCA remediation done | 2026-07-20 |  | In Progress |  | 2026-07-20 | false

## Budget
ProjectKey | Category | Budget | Forecast | Actual | Currency
ORB-1001 | Total | 1200000 | 1320000 | 840000 | EUR
ORB-1002 | Total | 480000 | 560000 | 505000 | EUR
ORB-1005 | Total | 640000 | 700000 | 470000 | EUR

## Resources
ProjectKey | Person | Role | AllocationPercent | CapacityPercent | OnLeave
ORB-1001 | Anna Berg | Project Management | 30 | 100 | false
ORB-1001 | Jonas Vik | Engineering | 80 | 100 | false
ORB-1001 | Priya Nair | Engineering | 100 | 100 | false
ORB-1002 | Anna Berg | Project Management | 25 | 100 | false
ORB-1002 | Sven Aalto | Engineering | 100 | 100 | false
ORB-1005 | Anna Berg | Project Management | 25 | 100 | false
ORB-1005 | Priya Nair | Engineering | 50 | 100 | false

## RAID
ProjectKey | Type | Description | Severity | Status
ORB-1002 | Risk | Legacy source data quality worse than profiled | Critical | Open
ORB-1001 | Risk | POS vendor API rate limits block rollout | High | Open
ORB-1005 | Issue | Certification auditor availability in August | Medium | Open

## Decisions
ProjectKey | Title | Status | Owner | NeededBy | Consequence
ORB-1002 | Approve revised go-live date (Aug 1) | Overdue | Steering Committee | 2026-06-20 | Cutover cannot be scheduled; team idle and client SLA at risk
ORB-1002 | Fund additional data-cleansing sprint | Pending | Client Sponsor | 2026-07-15 | Integrity errors persist into production
ORB-1001 | Choose caching approach for POS API limits | Pending | Jonas Vik | 2026-07-20 | Rollout throughput remains capped
ORB-1005 | Confirm external auditor firm | Approved | Anna Berg | 2026-06-30

## Scope
ProjectKey | Title | Type | Status | EffortImpactPct | DateRaised
ORB-1002 | Add real-time fraud checks | Add | Requested | 18 | 2026-07-05
ORB-1001 | Add loyalty module | Add | Approved | 10 | 2026-06-01
ORB-1005 | Drop legacy report export | Remove | Requested | -5 | 2026-07-08