## Decisions
project_id | decision_id | title | status | owner | raised_date | needed_by | consequence_if_delayed
ORB-1002 | D-1002-1 | Approve revised go-live date (Aug 1) | Overdue | Steering Committee | 2026-06-01 | 2026-06-20 | Cutover cannot be scheduled; team idle and client SLA at risk
ORB-1002 | D-1002-2 | Fund additional data-cleansing sprint | Pending | Client Sponsor | 2026-06-12 | 2026-07-15 | Integrity errors persist into production
ORB-1001 | D-1001-1 | Choose caching approach for POS API limits | Pending | Jonas Vik | 2026-05-25 | 2026-07-20 | Rollout throughput remains capped
ORB-1005 | D-1005-1 | Confirm external auditor firm | Pending | Anna Berg | 2026-06-05 | 2026-07-31 | Certification milestone slips
ORB-1006 | D-1006-1 | Approve data-ownership RACI | Approved | Lars Holm | 2026-05-02 | 2026-06-30