## Projects
Key | Name | PercentComplete | LastUpdated
ORB-1001 | Nordic Retail Platform | 40 | 2026-07-01
ORB-1002 | Customer Data Migration | 65 | 2026-06-15
ORB-1003 | AI Advisory Discovery | 55 | 2026-07-05
ORB-1004 | Warehouse Automation Rollout | 30 | 2026-06-28
ORB-1005 | Payments Compliance Upgrade | 72 | 2026-06-10
ORB-1006 | Data Governance Framework | 48 | 2026-07-03

## Milestones
ProjectKey | Name | DueDate | CompletedDate | Status | DependsOn
ORB-1001 | Requirements sign-off | 2026-02-27 | 2026-03-06 | Complete
ORB-1001 | POS pilot live | 2026-07-31 |  | In Progress
ORB-1001 | E-commerce go-live | 2026-09-15 |  | Not Started
ORB-1001 | All stores migrated | 2026-10-15 |  | Not Started
ORB-1002 | Profiling complete | 2026-01-30 | 2026-02-04 | Complete
ORB-1002 | Data cutover dress rehearsal | 2026-07-18 |  | Missed
ORB-1002 | Production cutover | 2026-08-01 |  | At Risk
ORB-1003 | Assessment delivered | 2026-06-20 | 2026-06-19 | Complete
ORB-1003 | Roadmap presented | 2026-07-15 |  | In Progress
ORB-1004 | Line commissioned | 2026-08-31 |  | In Progress
ORB-1005 | SCA remediation done | 2026-07-20 |  | In Progress
ORB-1005 | Certification achieved | 2026-08-15 |  | Not Started
ORB-1006 | Catalogue live | 2026-08-31 |  | In Progress

## Budget
ProjectKey | Category | Budget | Forecast | Actual
ORB-1001 | Total | 1200000 | 1320000 | 840000
ORB-1002 | Total | 480000 | 560000 | 505000
ORB-1003 | Total | 150000 | 148000 | 60000
ORB-1004 | Total | 2100000 | 2050000 | 690000
ORB-1005 | Total | 640000 | 700000 | 470000
ORB-1006 | Total | 380000 | 372000 | 150000

## Resources
ProjectKey | Person | Role | AllocationPercent | CapacityPercent | OnLeave
ORB-1001 | Anna Berg | Project Management | 30 | 100 | false
ORB-1001 | Jonas Vik | Engineering | 80 | 100 | false
ORB-1001 | Priya Nair | Engineering | 100 | 100 | false
ORB-1002 | Anna Berg | Project Management | 25 | 100 | false
ORB-1002 | Jonas Vik | Engineering | 60 | 100 | false
ORB-1002 | Sven Aalto | Engineering | 100 | 100 | false
ORB-1004 | Anna Berg | Project Management | 20 | 100 | false
ORB-1004 | Mette Sorensen | Delivery | 90 | 100 | false
ORB-1005 | Anna Berg | Project Management | 25 | 100 | false
ORB-1005 | Priya Nair | Engineering | 50 | 100 | false
ORB-1006 | Anna Berg | Project Management | 20 | 100 | false
ORB-1006 | Lars Holm | Advisory | 40 | 100 | false
ORB-1003 | Lars Holm | Advisory | 60 | 100 | false

## RAID
ProjectKey | Type | Description | Severity | Status
ORB-1002 | Risk | Legacy source data quality worse than profiled | Critical | Open
ORB-1002 | Risk | Cutover window may exceed agreed downtime | High | Open
ORB-1001 | Risk | POS vendor API rate limits block rollout | High | Open
ORB-1001 | Risk | Key-person dependency on PM across portfolio | High | Open
ORB-1004 | Risk | Robotics vendor lead time slippage | Medium | Open
ORB-1005 | Risk | Certification auditor availability in August | Medium | Open
ORB-1003 | Risk | Roadmap scope creep from stakeholders | Low | Open
ORB-1002 | Issue | Dress rehearsal failed - referential integrity errors | Critical | Open
ORB-1002 | Issue | Client sign-off on mapping rules delayed | High | Open
ORB-1001 | Issue | POS pilot store hardware not delivered | Medium | Open
ORB-1004 | Issue | Site power upgrade behind schedule | Medium | Open
ORB-1005 | Issue | Ambiguous SCA requirement interpretation | Low | Resolved

## ScopeWbs
project_id | wbs_code | parent_wbs | phase | task_name | depends_on_wbs | is_deliverable | deliverable_doc_required | base_estimate_hours | percent_complete | status
ORB-1001 | 1 |  |  | Nordic Retail Platform |  | No | No | 0 | 40 | In Progress
ORB-1001 | 1.1 | 1 | Discovery | Discovery & Requirements |  | Yes | Yes | 320 | 100 | Complete
ORB-1001 | 1.2 | 1 | Build | Store POS Integration | 1.1 | Yes | Yes | 900 | 55 | In Progress
ORB-1001 | 1.3 | 1 | Build | E-commerce Replatform | 1.1 | Yes | No | 1100 | 20 | In Progress
ORB-1001 | 1.4 | 1 | Rollout | Rollout & Hypercare | 1.2;1.3 | No | No | 400 | 0 | Not Started
ORB-1002 | 1 |  |  | Customer Data Migration |  | No | No | 0 | 65 | In Progress
ORB-1002 | 1.1 | 1 | Analyse | Source Data Profiling |  | Yes | Yes | 240 | 100 | Complete
ORB-1002 | 1.2 | 1 | Build | Mapping & Transformation | 1.1 | Yes | No | 600 | 80 | In Progress
ORB-1002 | 1.3 | 1 | Test | Cutover Rehearsal | 1.2 | Yes | Yes | 300 | 10 | At Risk
ORB-1002 | 1.4 | 1 | Cutover | Production Cutover | 1.3 | No | No | 180 | 0 | Not Started
ORB-1003 | 1 |  |  | AI Advisory Discovery |  | No | No | 0 | 55 | In Progress
ORB-1003 | 1.1 | 1 | Assess | Current-State Assessment |  | Yes | Yes | 180 | 90 | In Progress
ORB-1003 | 1.2 | 1 | Plan | Opportunity Roadmap | 1.1 | Yes | Yes | 180 | 30 | In Progress
ORB-1004 | 1 |  |  | Warehouse Automation Rollout |  | No | No | 0 | 30 | In Progress
ORB-1004 | 1.1 | 1 | Build | Conveyor & Robotics Install |  | Yes | No | 1400 | 45 | In Progress
ORB-1004 | 1.2 | 1 | Build | WMS Integration | 1.1 | Yes | No | 700 | 15 | In Progress
ORB-1005 | 1 |  |  | Payments Compliance Upgrade |  | No | No | 0 | 72 | In Progress
ORB-1005 | 1.1 | 1 | Build | PSD2/SCA Remediation |  | Yes | No | 600 | 85 | In Progress
ORB-1005 | 1.2 | 1 | Certify | Audit & Certification | 1.1 | Yes | Yes | 240 | 40 | In Progress
ORB-1006 | 1 |  |  | Data Governance Framework |  | No | No | 0 | 48 | In Progress
ORB-1006 | 1.1 | 1 | Build | Data Catalogue |  | Yes | No | 480 | 60 | In Progress
ORB-1006 | 1.2 | 1 | Govern | Policy & Ownership | 1.1 | Yes | Yes | 300 | 35 | In Progress

## TimeUsed
project_id | resource_name | wbs_code | week_starting | registered_hours | entry_type | notes
ORB-1001 | Jonas Vik | 1.2 | 2026-06-08 | 38 | Work | POS adapter build
ORB-1001 | Jonas Vik | 1.2 | 2026-06-15 | 40 | Work | POS adapter build
ORB-1001 | Priya Nair | 1.3 | 2026-06-15 | 42 | Work | Checkout UI
ORB-1001 | Anna Berg | 1.2 | 2026-06-15 | 6 | Work | PM oversight
ORB-1002 | Sven Aalto | 1.3 | 2026-06-08 | 45 | Work | Rehearsal prep - overtime
ORB-1002 | Sven Aalto | 1.3 | 2026-06-15 | 44 | Work | Rehearsal prep - overtime
ORB-1002 | Jonas Vik | 1.2 | 2026-06-15 | 18 | Work | Split with ORB-1001
ORB-1002 | Anna Berg | 1.2 | 2026-06-15 | 0 | Blocked day | Holiday 2026-06-16 to 2026-06-27
ORB-1004 | Mette Sorensen | 1.1 | 2026-06-15 | 40 | Work | Commissioning
ORB-1005 | Priya Nair | 1.1 | 2026-06-15 | 20 | Work | SCA remediation
ORB-1003 | Lars Holm | 1.1 | 2026-06-15 | 22 | Work | Assessment write-up

## Decisions
project_id | decision_id | title | status | owner | raised_date | needed_by | consequence_if_delayed
ORB-1002 | D-1002-1 | Approve revised go-live date (Aug 1) | Overdue | Steering Committee | 2026-06-01 | 2026-06-20 | Cutover cannot be scheduled; team idle and client SLA at risk
ORB-1002 | D-1002-2 | Fund additional data-cleansing sprint | Pending | Client Sponsor | 2026-06-12 | 2026-07-15 | Integrity errors persist into production
ORB-1001 | D-1001-1 | Choose caching approach for POS API limits | Pending | Jonas Vik | 2026-05-25 | 2026-07-20 | Rollout throughput remains capped
ORB-1005 | D-1005-1 | Confirm external auditor firm | Pending | Anna Berg | 2026-06-05 | 2026-07-31 | Certification milestone slips
ORB-1006 | D-1006-1 | Approve data-ownership RACI | Approved | Lars Holm | 2026-05-02 | 2026-06-30