## RAID
ProjectKey | Type | Description | Severity | Status
ORB-1002 | Risk | Legacy source data quality worse than profiled | Critical | Open
ORB-1002 | Risk | Cutover window may exceed agreed downtime | High | Open
ORB-1001 | Risk | POS vendor API rate limits block rollout | High | Open
ORB-1001 | Risk | Key-person dependency on PM across portfolio | High | Open
ORB-1004 | Risk | Robotics vendor lead time slippage | Medium | Open
ORB-1005 | Risk | Certification auditor availability in August | Medium | Open
ORB-1003 | Risk | Roadmap scope creep from stakeholders | Low | Open
ORB-1002 | Issue | Dress rehearsal failed - referential integrity errors | Critical | Open
ORB-1002 | Issue | Client sign-off on mapping rules delayed | High | Open
ORB-1001 | Issue | POS pilot store hardware not delivered | Medium | Open
ORB-1004 | Issue | Site power upgrade behind schedule | Medium | Open
ORB-1005 | Issue | Ambiguous SCA requirement interpretation | Low | Resolved