## ScopeWbs
project_id | wbs_code | parent_wbs | phase | task_name | depends_on_wbs | is_deliverable | deliverable_doc_required | base_estimate_hours | percent_complete | status
ORB-1001 | 1 |  |  | Nordic Retail Platform |  | No | No | 0 | 40 | In Progress
ORB-1001 | 1.1 | 1 | Discovery | Discovery & Requirements |  | Yes | Yes | 320 | 100 | Complete
ORB-1001 | 1.2 | 1 | Build | Store POS Integration | 1.1 | Yes | Yes | 900 | 55 | In Progress
ORB-1001 | 1.3 | 1 | Build | E-commerce Replatform | 1.1 | Yes | No | 1100 | 20 | In Progress
ORB-1001 | 1.4 | 1 | Rollout | Rollout & Hypercare | 1.2;1.3 | No | No | 400 | 0 | Not Started
ORB-1002 | 1 |  |  | Customer Data Migration |  | No | No | 0 | 65 | In Progress
ORB-1002 | 1.1 | 1 | Analyse | Source Data Profiling |  | Yes | Yes | 240 | 100 | Complete
ORB-1002 | 1.2 | 1 | Build | Mapping & Transformation | 1.1 | Yes | No | 600 | 80 | In Progress
ORB-1002 | 1.3 | 1 | Test | Cutover Rehearsal | 1.2 | Yes | Yes | 300 | 10 | At Risk
ORB-1002 | 1.4 | 1 | Cutover | Production Cutover | 1.3 | No | No | 180 | 0 | Not Started
ORB-1003 | 1 |  |  | AI Advisory Discovery |  | No | No | 0 | 55 | In Progress
ORB-1003 | 1.1 | 1 | Assess | Current-State Assessment |  | Yes | Yes | 180 | 90 | In Progress
ORB-1003 | 1.2 | 1 | Plan | Opportunity Roadmap | 1.1 | Yes | Yes | 180 | 30 | In Progress
ORB-1004 | 1 |  |  | Warehouse Automation Rollout |  | No | No | 0 | 30 | In Progress
ORB-1004 | 1.1 | 1 | Build | Conveyor & Robotics Install |  | Yes | No | 1400 | 45 | In Progress
ORB-1004 | 1.2 | 1 | Build | WMS Integration | 1.1 | Yes | No | 700 | 15 | In Progress
ORB-1005 | 1 |  |  | Payments Compliance Upgrade |  | No | No | 0 | 72 | In Progress
ORB-1005 | 1.1 | 1 | Build | PSD2/SCA Remediation |  | Yes | No | 600 | 85 | In Progress
ORB-1005 | 1.2 | 1 | Certify | Audit & Certification | 1.1 | Yes | Yes | 240 | 40 | In Progress
ORB-1006 | 1 |  |  | Data Governance Framework |  | No | No | 0 | 48 | In Progress
ORB-1006 | 1.1 | 1 | Build | Data Catalogue |  | Yes | No | 480 | 60 | In Progress
ORB-1006 | 1.2 | 1 | Govern | Policy & Ownership | 1.1 | Yes | Yes | 300 | 35 | In Progress