## Milestones
ProjectKey | Name | DueDate | CompletedDate | Status | DependsOn
ORB-1001 | Requirements sign-off | 2026-02-27 | 2026-03-06 | Complete
ORB-1001 | POS pilot live | 2026-07-31 |  | In Progress
ORB-1001 | E-commerce go-live | 2026-09-15 |  | Not Started
ORB-1001 | All stores migrated | 2026-10-15 |  | Not Started
ORB-1002 | Profiling complete | 2026-01-30 | 2026-02-04 | Complete
ORB-1002 | Data cutover dress rehearsal | 2026-07-18 |  | Missed
ORB-1002 | Production cutover | 2026-08-01 |  | At Risk
ORB-1003 | Assessment delivered | 2026-06-20 | 2026-06-19 | Complete
ORB-1003 | Roadmap presented | 2026-07-15 |  | In Progress
ORB-1004 | Line commissioned | 2026-08-31 |  | In Progress
ORB-1005 | SCA remediation done | 2026-07-20 |  | In Progress
ORB-1005 | Certification achieved | 2026-08-15 |  | Not Started
ORB-1006 | Catalogue live | 2026-08-31 |  | In Progress