Project: ORB-1002

Steering Committee — ORB-1002 Customer Data Migration

Date: 2026-06-18

Attendees: Anna Berg (PM, dialling in — on holiday from 2026-06-16 to 2026-06-27), Sven Aalto (Migration Specialist), Client Sponsor (M. Larsen), NextWave PMO (observer)

Status: Project is Red. The data cutover dress rehearsal (milestone M-1002-2), baselined for 2026-05-30, did not pass — referential integrity errors surfaced across ~4% of customer records once transformation rules ran end to end. This is worse than the profiling report suggested back in March. Rehearsal is now forecast for 2026-07-18 at the earliest.

Budget: Spend has crossed the planned €480k (actuals at €505k) and the forecast at completion is now €560k — roughly a 17% overrun. Driver is unplanned overtime on data cleansing plus a likely extra cleansing sprint.

Key point: Sven flagged that the legacy source quality risk (R-1002-1) is materialising and still has no agreed mitigation — needs an owner decision this week.

Key point: With Anna on leave for two weeks and also covering four other projects, the committee noted the team is exposed to a key-person dependency. Cover arrangements were not settled.

Key point: Client sign-off on the mapping rules is still outstanding, blocking the rehearsal re-run.

Decision needed D-1002-1 (OVERDUE): approve the revised go-live date of 2026-08-01. Was needed by 2026-06-20. Until approved, cutover cannot be scheduled and the delivery team sits idle.

Decision needed D-1002-2: fund an additional data-cleansing sprint (~€60k). Sponsor to decide by 2026-07-15.

Action: Circulate integrity-error breakdown to sponsor — Sven Aalto — due 2026-06-20.

Action: Secure PM cover for holiday period — Anna Berg — due 2026-06-19.

Action: Confirm go-live date decision — Steering Committee — due 2026-06-20.